## English
Release burndown | Here a release means completing an agreed version of your product that has an agreed deadline. This tools helps you track the fullfillment of this agreement.
Versions are typically larger chunks of functionality that combined deliver a significant value and have been agreed
Type the real story points into the ACTUAL row, starting with sprint 0. Then set the two yellow cells below.
Everything else is calculated. The forecast is one straight line starting at your last real value, so every forecast cell uses the identical formula.
SETTINGS (edit the two yellow cells only)
1. Data is fixed up to and including sprint | 5 | <- the last sprint you have real numbers for
2. Rate is measured over the last ... sprints | 3 | <- how many sprints of change feed the rate. 3 sprints = 4 data points
-> Forecast starts at sprint | 6
-> First sprint used to measure the rate | 2 | <- sprint 0 sits in the first data column, so a sprint number is also its column offset
-> Sprints used to measure the rate | 2 to 5
-> Story points left at sprint B8 (forecast starts here) | 394
-> Burn-down rate: change in story points left per sprint | -24.9 | <- NOT velocity. This is how fast the remaining scope shrinks, which also includes descoping, added scope and re-estimation
-> Forecast reaches 0 story points at sprint | 20.8233
-> Check | OK
DATA
Sprint nr | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Story points left at sprint - ACTUAL (type here) | 501 | 473 | 470 | 459 | 438 | 394
Story points left at sprint - ACTUAL + FORECAST (chart) | 501 | 473 | 470 | 459 | 438 | 394 | 369.1 | 344.2 | 319.3 | 294.4 | 269.5
To add more sprints | Select the last column (L), copy it to the right, and continue the sprint numbering: 11, 12, 13 and so on. Nothing else needs to change, because every forecast cell holds the same formula and the settings are absolute references.
Only remember to extend both chart data ranges to the new last column: the bars read the ACTUAL row, the line reads the ACTUAL + FORECAST row.
How to read the forecast row | If the sprint number is not past setting 1, show the actual value. Otherwise: story points left at the fixed sprint, plus the rate for every sprint since then.
The forecast therefore always starts exactly on your last real data point. There is no jump in the chart where actual turns into forecast.
Actual values typed in after the fixed sprint are ignored by the forecast on purpose, but they DO appear as bars. That is the point: the bars show where you really are, the line shows the forecast you froze at the fixed sprint.
Sprint 0 is the starting point before any sprint has run. It must be filled in. Example values 150 / 130 / 100 / 100 are placeholders, replace them with your own.
Note on C28: The actual story points left at the fixed sprint. OFFSET jumps B8 columns right from sprint 0. The forecast line starts exactly here, so there is no jump in the chart.
Note on C29: SLOPE over the window: sprints B11 to B8, which is B9+1 data points. Negative means the remaining scope is shrinking. Deliberately not called velocity: velocity counts work completed by the team, while this number also moves when scope is cut, added or re-estimated.